## Iteration 1
Product Backlog | [11 empty] | Sprint Backlog
ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS |  | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED
#1 | Splash Screen | 5 | 3 | Completed |  | 3 | 0 |  |  |  |  | #1 | Splash Screen | İsmetcan Hergünşen | 3 | COMPLETED
#2 | Menu | 5 | 5 | Completed |  | 5 | 0 |  |  |  |  | #2 | Menu | Gamze Küçükçolak | 5 | COMPLETED
#3 | Creating Profile | 1 | 4 | Not Started |  | 4 | 4 | [6 empty] | WEEK1 SUM | 8
#4 | Saving Profile | 1 | 8 | Not Started |  | 8 | 8
#5 | Privacy Settings | 2 | 6 | Not Started |  | 6 | 6
#6 | Notifications | 4 | 8 | Not Started |  | 8 | 8
#7 | Tones | 5 | 4 | Not Started |  | 4 | 4
#8 | Insert Map | 1 | 5 | Not Started |  | 5 | 5
#9 | Show contacts on map | 1 | 5 | Not Started |  | 5 | 5
#10 | Show distances btw contacts | 3 | 5 | Not Started |  | 5 | 5
#11 | Add Contacts | 3 | 8 | Not Started |  | 8 | 8
#12 | View Contacts Information | 2 | 3 | Not Started |  | 3 | 3
| TOTAL TIME |  | 64 |  | TOTAL | 64 | 56