## Iteration 1
Product Backlog | [11 empty] | Sprint Backlog
ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS |  | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED | Group Members | Nazlı Karalar
#1 | Splash Screen | 5 | 3 | Completed |  | 3 | 0 |  |  |  |  | #1 | Splash Screen | İsmetcan Hergünşen | 3 | COMPLETED |  | İsmetcan Hergünşen
#2 | Menu | 5 | 5 | Completed |  | 5 | 0 |  |  |  |  | #2 | Menu | Gamze Küçükçolak | 5 | COMPLETED |  | Gamze Küçükçolak
#3 | Creating Profile | 1 | 4 | Not Started |  | 4 | 4 | [6 empty] | WEEK1 SUM | 8 |  |  | Mehmet Kağan Kayaalp
#4 | Saving Profile | 1 | 8 | Not Started |  | 8 | 8 | [10 empty] | Erdi Koç
#5 | Privacy Settings | 2 | 6 | Not Started |  | 6 | 6
#6 | Notifications | 4 | 8 | Not Started |  | 8 | 8
#7 | Tones | 5 | 4 | Not Started |  | 4 | 4
#8 | Insert Map | 1 | 5 | Not Started |  | 5 | 5
#9 | Show contacts on map | 1 | 5 | Not Started |  | 5 | 5
#10 | Show distances btw contacts | 3 | 5 | Not Started |  | 5 | 5
#11 | Add Contacts | 3 | 8 | Not Started |  | 8 | 8
#12 | View Contacts Information | 2 | 3 | Not Started |  | 3 | 3
| TOTAL TIME |  | 64 |  | TOTAL | 64 | 56

## Iteration 2
Product Backlog | [11 empty] | Sprint Backlog
ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS |  | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED | Group Members | Nazlı Karalar
#1 | Splash Screen | 5 | 3 | Completed |  | 3 | 0 | [6 empty] | Nazlı Karalar | 3 | COMPLETED |  | İsmetcan Hergünşen
#2 | Menu | 5 | 5 | Completed |  | 5 | 0 | [6 empty] | Erdi Koç | 5 | COMPLETED |  | Gamze Küçükçolak
#3 | Creating Profile | 1 | 4 | Not Started |  | 4 | 4 | [6 empty] | Mehmet Kağan Kayaalp |  | COMPLETED |  | Mehmet Kağan Kayaalp
#4 | Saving Profile | 1 | 8 | Not Started |  | 8 | 8 | [6 empty] | WEEK1 SUM | 8 |  |  | Erdi Koç
#5 | Settings | 2 | 6 | Not Started |  | 6 | 6
#6 |  |  |  | Not Started
#7 |  |  |  | Not Started
#8 |  |  |  | Not Started
#9 | Notifications | 4 | 8 | Not Started |  | 8 | 8
#10 | Tones | 5 | 4 | Not Started |  | 4 | 4
#11 | Insert Map | 1 | 5 | Not Started |  | 5 | 5
#12 | Show contacts on map | 1 | 5 | Not Started |  | 5 | 5
#13 | Show distances btw contacts | 3 | 5 | Not Started |  | 5 | 5
#14 | Add Contacts | 3 | 8 | Not Started |  | 8 | 8
#15 | View Contacts Information | 2 | 3 | Not Started |  | 3 | 3
| TOTAL TIME |  | 64 |  | TOTAL | 64 | 56