## Iteration 1
Product Backlog | [11 empty] | Sprint Backlog
ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS |  | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED | Group Members | Nazlı Karalar
#1 | Splash Screen | 5 | 3 | Completed |  | 3 | 0 |  |  |  |  | #1.1 | Uploading Logo Picture | İsmetcan Hergünşen | 2 | COMPLETED |  | İsmetcan Hergünşen
#2 | Menu | 5 | 5 | Completed |  | 5 | 0 |  |  |  |  | #1.2 | Fade in Logo | Gamze Küçükçolak | 1 | COMPLETED |  | Gamze Küçükçolak
#3 | Creating Profile | 1 | 4 | Not Started |  | 4 | 4 |  |  |  |  | #2.1 | Uploading Menu Photos | İsmetcan Hergünşen | 4 | COMPLETED |  | Mehmet Kağan Kayaalp
#4 | Saving Profile | 1 | 8 | Not Started |  | 8 | 8 |  |  |  |  | #2.2 | Adding Buttons in Menu | Nazlı Karalar | 1 | COMPLETED |  | Erdi Koç
#5 | Privacy Settings | 2 | 6 | Not Started |  | 6 | 6 | [6 empty] | WEEK1 SUM | 8
#6 | Notifications | 4 | 8 | Not Started |  | 8 | 8
#7 | Tones | 5 | 4 | Not Started |  | 4 | 4
#8 | Insert Map | 1 | 5 | Not Started |  | 5 | 5
#9 | Show contacts on map | 1 | 5 | Not Started |  | 5 | 5
#10 | Show distances btw contacts | 3 | 5 | Not Started |  | 5 | 5
#11 | Add Contacts | 3 | 8 | Not Started |  | 8 | 8
#12 | View Contacts Information | 2 | 3 | Not Started |  | 3 | 3
| TOTAL TIME |  | 64 |  | TOTAL | 64 | 56

## Iteration 2
Product Backlog | [11 empty] | Sprint Backlog
ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS |  | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED | Group Members | Nazlı Karalar
#1 | Splash Screen | 5 | 3 | Completed |  | 3 | 0 | 0 |  |  |  | #5.1 | Start Automatically | Erdi Koç | 2 | COMPLETED |  | İsmetcan Hergünşen
#2 | Menu | 5 | 5 | Completed |  | 5 | 0 | 0 |  |  |  | #5.2 | Send my location | Mehmet Kağan Kayaalp | 2 | COMPLETED |  | Gamze Küçükçolak
#3 | Creating Profile | 1 | 4 | Not Started |  | 4 | 4 | 4 |  |  |  | #6.1 | Notify People around Here | Nazlı Karalar | 2 | COMPLETED |  | Mehmet Kağan Kayaalp
#4 | Saving Profile | 1 | 8 | Not Started |  | 8 | 8 | 8 |  |  |  | #6.2 | Distance Measurement | Gamze Küçükçolak | 2 | COMPLETED |  | Erdi Koç
#5 | Privacy Settings | 2 | 6 | Completed |  | 6 | 6 | 0 |  |  |  | #6.3 | Connection distances with button | Erdi Koç | 2 | COMPLETED
#6 | Notifications | 4 | 8 | Completed |  | 8 | 8 | 0 |  |  |  | #7.1 | Notification Tone | Mehmet Kağan Kayaalp | 2 | COMPLETED
#7 | Tones | 5 | 4 | Completed |  | 4 | 4 | 0 | [5 empty] | WEEK2 SUM | 12
#8 | Insert Map | 1 | 5 | Not Started |  | 5 | 5 | 5
#9 | Show contacts on map | 1 | 5 | Not Started |  | 5 | 5 | 5
#10 | Show distances btw contacts | 3 | 5 | Not Started |  | 5 | 5 | 5
#11 | Add Contacts | 3 | 8 | Not Started |  | 8 | 8 | 8
#12 | View Contacts Information | 2 | 3 | Not Started |  | 3 | 3 | 3
| TOTAL TIME |  | 64 |  | TOTAL | 64 | 56 | 44

## Iteration 3
Product Backlog | [11 empty] | Sprint Backlog
ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS |  | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED | Group Members | Nazlı Karalar
#1 | Splash Screen | 5 | 3 | Completed |  | 3 | 0 | 0 | 0 |  |  | #3.1 | Profile Information Button | Mehmet Kağan Kayaalp | 2 | COMPLETED |  | İsmetcan Hergünşen
#2 | Menu | 5 | 5 | Completed |  | 5 | 0 | 0 | 0 |  |  | #3.2 | Adding Friends Button | Gamze Küçükçolak | 2 | COMPLETED |  | Gamze Küçükçolak
#3 | Creating Profile | 1 | 4 | Completed |  | 4 | 4 | 4 | 0 |  |  | #3.3 | Assign Ids to the buttons | İsmetcan Hergünşen | 1 | COMPLETED |  | Mehmet Kağan Kayaalp
#4 | Saving Profile | 1 | 8 | Completed |  | 8 | 8 | 8 | 0 |  |  | #4.1 | Creating Database | Nazlı Karalar | 6 | COMPLETED |  | Erdi Koç
#5 | Privacy Settings | 2 | 6 | Completed |  | 6 | 6 | 0 | 0 |  |  | #4.2 | Connecting Profile Information with Database | Erdi Koç | 4 | COMPLETED
#6 | Notifications | 4 | 8 | Completed |  | 8 | 8 | 0 | 0 |  |  | #4.3 | Saving Profile | Nazlı Karalar | 2 | COMPLETED
#7 | Tones | 5 | 4 | Completed |  | 4 | 4 | 0 | 0 |  |  |  |  | WEEK2 SUM | 17
#8 | Insert Map | 1 | 5 | Not Started |  | 5 | 5 | 5 | 5
#9 | Show contacts on map | 1 | 5 | Not Started |  | 5 | 5 | 5 | 5
#10 | Show distances btw contacts | 3 | 5 | Not Started |  | 5 | 5 | 5 | 5
#11 | Add Contacts | 3 | 8 | Not Started |  | 8 | 8 | 8 | 8
#12 | View Contacts Information | 2 | 3 | Not Started |  | 3 | 3 | 3 | 3
| TOTAL TIME |  | 64 |  | TOTAL | 64 | 56 | 39 | 26
[8 empty] | Expected Time | 12
[8 empty] | Rest | 5
[5 empty] | ACTUAL TOTAL |  | 64 | 56 | 44 | 49 | 37